## Sheet1
DATE | TASK SUMMARY | TIME SPENT ON THE TASKS | STATUS
2020-07-15 | Attended the meeting at 10 AM TO 10.30 Attended the client meeting at 11.30 am to | 30min 30min

## sprint1testplan
Feature # | Feature / Epic Details | Story # | Story Details | Story Estimation | DoD | Dependencies
(Person Hours)
1 | Support visibility and enum rules part of the report template document(Reporting Service : 56200) | 1 | Each device type need to display a enum values based on the numeric value coming from the report data, this can be part of the type definition itself |  | 1) The Rest API shall be cable on incorporating enum rules as Jason format | One JS now,
Type definition Json has to be incorporated ?
[5 empty] | 2) Convert the data in report as mentioned in Enum files(eg: if 1 True else False) | REST END Points modification.
|  | 2 | Based on certain condition of a parameter, another parameter or group of parameter should be made visible/hidden. This JSON template shall be consumed |  | 1) The Rest API shall be cable on incorporating visibility rules as Jason format. | This JSON template shall be consumed is it report template?
2) Based on the rules a field or set of fields shall be made visible or not.
2 | Lightweight report template common for device types(Reporting Service : 55201) | 3 | Report generation component shall generate the report based on the hierarchy of data passed across with the lightweight report template that is common across all device types. |  | 1) Rest shall be capable of handling Light weight template. | Can we have a generic template.
2) The report generated using Light weight template is dynamic based on the data from JSON file based on grouping.
3 | Option to choose lightweight common template or device type specific detail template.(Reporting Service : 56230) | 4 |  |  |  | 1) With JSON
2) Report Template
4 | Support for plugin for device type(Reporting Service : 56231) | 5 | Report generation component shall support for custom report component if the reporting requirements are very specific to a device type and can not be (TBD)
|  | 6 | Sample Plugin with minimal implimentation to prove the Plugin interface is working |  | Micro service shall be capable of adding plugins so that only input data JSON and report template shall be taken as input and implementation of report generation logic can be recreated using custom implementation. | 1) Which level of plugable is expected from service layer or Bottom layer
2) a) Depandancy injection
b) Fluent i/f pattern
c) Middle ware segrigation with grapecity etc.
5 | Detailed Study of Existing System | 7 | DB details and entire system flow in detail |  | High Level Design Document of Legacy code checked in repo after final review.
6 | Benchmarking new Report library | 8 | Benchmarking new Report library
7 | Test Case Prepration | 9 | Test Case Prepration
8 | Test Execution | 10 | Test Execution
9 | Automated Test Frame work Proto | 11 | Automated Test Frame work Proto

## Sheet3
| 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14
Adithya | Backlog Sprint 0 | Backlog Sprint 0 | Story 4 | Story 4 | Story 4 |  |  | Story 6 |  | Story 6 | BugFix Support | Sprint 3 Planning
Chethan | Backlog Sprint 0 | Backlog Sprint 0 | Story 7 | Story 7 | Story 8 |  |  | Story 8 |  | Story 8 | BugFix Support
Shridevi | 2020-08-03: Backlog Sprint 0; 2020-08-04: Backlog Sprint 0; 2020-08-05: Story 1; 2020-08-06: Story 1; 2020-08-07: Story 2; 2020-08-10: Story 2; 2020-08-12: Bugfix Support
Anusha | 2020-08-03: Backlog Sprint 0; 2020-08-04: Backlog Sprint 0; 2020-08-05: Story 1; 2020-08-06: Story 1; 2020-08-07: Story 3; 2020-08-10: Story 3; 2020-08-12: Bugfix Support
Akshitha | Backlog Sprint 0 | Backlog Sprint 0 | Story 4 | Story 4 | Story 4 |  |  | Story 6 |  | Story 6 | BugFix Support
Deepak | Backlog Sprint 0 | Backlog Sprint 0 | Story 7 | Story 7 | Story 8 |  |  | Story 8 |  | Story 8 | BugFix Support
Mahadevi | Backlog Sprint 0 | Backlog Sprint 0 | Story 9 | Story 9 | Story 9 |  |  | Story 11 |  | Story 10 | Story 10
Hemalatha | Backlog Sprint 0 | Backlog Sprint 0 | Story 11 | Story 11 | Story 9 |  |  | Story 10 |  | Story 10 | Story 10

## sprnt1Execution
Feature # | Feature / Epic Details | Story # | Story Details | Story Estimation | DoD | Dependencies
(Person Hours)
1 | AKS high level analysis | 1 | Identify the cost involved, limitations and prepare report based on this. |  | Prepare and Present the document to customer and mutually agreed
2 | Existing System Study | 2 | Detailed Study of Existing system with respect to integration of Report service |  | One pager to describe the impact of current integration plan and effort for Controller or Adapter modules checked in at TFS after mutual agreement
3 | Integration with Current Code base flow | 3 | Integration with CGA device type (Analyser) |  | Successful execution of Integration Test cases that impact CGA Device Type and Report App.
|  | 4 | Integration with PGC (device type) work flow |  | Successful execution of Integration Test cases that impact PGC Device Type and Report App.
|  | 4.1 | Integration with FPTA (device type) work flow |  | Successful execution of Integration Test cases that impact FPTA Device Type and Report App.
|  | 5 | Integration with Process Master (device type) work flow |  | Successful execution of Integration Test cases that impact Process Master Device Type and Report App.
|  | 6 | Additional Controllers/Test app to be developed for seamless integration. |  | Development and sign of Additional signoff as Agreed by Story 1
4 | Integration Testing | 7 | Analysing the revising the existing test cases of Legacy system |  | -
|  | 8 | Addition or modification aligned to integration. |  | Updating the agreed Integration Test cases in TFS.
|  | 9 | Integration Testing based on the agreed test cases and bug fixing. |  | Updating the Test result in TFS.
All the test cases should be passed or if differed or failed should be mutually agreed
5 | Test Automation | 10 | A full fledged Test automation framework capable of executing all rest APIs |  | All API Enpoints should be running with the framework and sucess.
6 | MQTT Brocker Study | 11 | MQTT Brocker POC, includes send recieve data to Mosquito Brocker |  | Message subscription and listening should be done with C# Code
7 | Mongo INtegration to Report App | 12 | Mongo Integration includes defining Db and basic opration and integration to Report App microservice |  | Template upload and Report generation should happen and links should be though Mongo DB.
8 | Issues reported by TE while sprint 1 testing by Customer and testing team | 13 | Validation Bug Fix & Overrite Issue by Customer |  | All the validation bugs and customer reported bugs should be tested against the test case and should be sucess.
10 | Customer suggestions | 14 | Change Device ID to Device Type and align the flow |  | Should be tested in Swagger with end to end and all respective TC should be updated and PASS
|  | 15 | Return pdf report insted of filelocation |  | PDF report should come as output or return to the generate report API and validated against the respective test cases and should be success
|  | 16 | Chaing API end poinst for Upload Report template and update the flow |  | Upload template should take flexer file and or type definition json file and upload teh template and tc should be pass
|  | 17 | Chaing API end poinst for Generate report Report and align the flow |  | Generate Report API should take respective json file and generate report and respective TC should be pass

## Sheet4
CLARIFICATION SHEET
No | Query | Origin (if possible) | Query Addressed By | Status | Query Date | Close Date | Clarification | Remarks
1 | More details on CGA device type | Sprint Discussion
2 | PGC (device type) work flow
3 | FPTA (device type) work flow

## Sheet5
| Sprint Start | [8 empty] | Sprint Development Ends
Testing Ends
| 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28
John | 2020-08-17: Backlog Sprint 1; 2020-08-18: Story 1; 2020-08-19: Story 2; 2020-08-24: story 20; 2020-08-28: Sprint 2 Planning
Adithya | Backlog Sprint 1 | Backlog Sprint 0 | Backlog Sprint 0 | Leave | Story 1 |  |  | Story 19 | Story 1 | Story 19 | Story 1
Chethan | Backlog Sprint 1 | Story 2 | Story 2 | Story 2 | Leave |  |  | Story 6 | Story 6 |  | Bugfix
Shridevi | Backlog Sprint 1 | Story 3 | Story 13 | Story 13 | Story 13 |  |  | Story 6 | Story 6 |  | Bugfix
Anusha | Backlog Sprint 1 | Story 3 | Story 14 | Story 14 | Story 14 |  |  | story 20 | Story 23 | Story 23 | Bugfix
Akshitha | Backlog Sprint 1 | Story 1 | Story 11 | Story 11 | Story 11 |  |  | Story 11 | Story 23 | Story 23 | Bugfix
Deepak | Backlog Sprint 1 | Story 2 | Story 12 | Story 18 | Leave |  |  | Leave | Leave | Leave | Leave
Mahadevi | Backlog Sprint 1 | Backlog Sprint 0 | Story 10 | Story 7 | Story 7 |  |  | Story 9 | Story 9 | Story 9 | Story 9
Hemalatha | Backlog Sprint 1 | Backlog Sprint 0 | Story 10 | Story 10 | Story 8 |  |  | Story 8 | Story 10 | Story 9 | Story 9
Adithya SM | Backlog Sprint 1 | Story 2 | Story 16 | Story 17 | Story 17 |  |  | Story 17 | Story 17 | Story 21
Arun T | Backlog Sprint 1 | Story 2 | Story 15 | Story 15 | Story 15 |  |  | story 20 | story 20 | Story 22